## Sheet1
Phase | Main Activity | Sub-Activity | Estimated Effort | Start date | End date | Actual Effort
Design | Use -case identification | Use-case diagram | 4 | 2010-09-01 | 2010-10-01 | 5
| Activity diagram |  | 7 | 2010-11-01 | 2010-12-01 | 5
| Interaction Diagram | Sequence diagram | 8 | 13/1/2010 | 14/1/2010 | 5
| Class diagram |  | 6 | 15/1/2010 | 16/1/2010 | 5
|  |  | 25 |  |  | 20
Implementation | UI Design | Homepage - Login | 2 | 18/1/2010 | 18/1/2010 | 2
|  | Registration | 1 | 18/1/2010 | 18/1/2010 | 2
|  | CRUD Training | 1 | 19/1/2010 | 19/1/2010 | 1
|  | CRUD Crop | 1 | 19/1/2010 | 19/1/2010 | 2
|  | CRUD Fertilizer/Soil | 1 | 21/1/2010 | 21/1/2010 | 1
|  | CRUD Location | 1 | 21/1/2010 | 21/1/2010 | 2
|  | CRUD Loan Schemes | 1 | 22/1/2010 | 22/1/2010 | 1
|  | CRUD Insurance Schemes | 1 | 22/1/2010 | 22/1/2010 | 1
|  | CRUD Polls | 2 | 24/1/2010 | 24/1/2010 | 3
|  | CRUD Tool | 1 | 25/1/2010 | 25/1/2010 | 1
|  | CRUD Queries | 1 | 25/1/2010 | 25/1/2010 | 1
|  | User-Poll interaction | 1 | 27/1/2010 | 27/1/2010 | 1
|  | User-Crop interaction | 1 | 28/1/2010 | 28/1/2010 | 1
|  | User-Training interaction | 1 | 29/1/2010 | 29/1/2010 | 1
|  | User-Query interaction | 1 | 29/1/2010 | 29/1/2010 | 1
|  | User-Loan interaction | 1 | 30/1/2010 | 30/1/201 | 1
|  | User-Interation interaction | 1 | 30/1/2010 | 30/1/2010 | 1
|  | Reports - including PDF generation | 1 | 31/1/2010 | 31/1/2010 | 1
|  | Add Officers | 0.5 | 31/1/2010 | 31/1/2010 | 0.5
|  |  | 20.5 |  |  | 24.5
| System Config Files + Listener + Interceptor |  | 10 | 2010-03-02 | 2010-07-02 | 12.5
Class Design + Implementation | Actions + Beans | LoginAction | 1.5 | 2010-08-02 | 2010-08-02 | 1.5
|  | AccountAction | 2 | 2010-09-02 | 2010-09-02 | 2
|  | RegisterAction | 2 | 2010-10-02 | 2010-11-02 | 2.5
|  | FertAction | 2 | 2010-11-02 | 2010-12-02 | 2
|  | InsAction | 2 | 13/2/2010 | 13/2/2010 | 1.5
|  | LoanAction | 2 | 13/2/2010 | 14/2/2010 | 1.5
|  | LocAction | 3 | 14/2/2010 | 15/2/2010 | 3
|  | PollAction | 1.5 | 16/2/2010 | 16/2/2010 | 2
|  | ToolAction | 1.5 | 17/2/2010 | 17/2/2010 | 2
|  | SoilAction | 1 | 19/2/2010 | 19/2/2010 | 0.5
|  | TrainingAction | 2.5 | 19/2/2010 | 20/2/2010 | 2.5
|  | CropAction | 3.5 | 20/2/2010 | 22/2/2010 | 4
|  | MarketAction | 2 | 25/2/2010 | 25/2/2010 | 2
|  | QueryAction | 2 | 27/2/2010 | 27/2/2010 | 1.5
|  | ReportAction | 1.5 | 2010-01-03 | 2010-02-03 | 2
|  |  | 30 |  |  | 30.5
Class Design + Implementation | DAO Interface + DAO Implementation + BSO + SQL code | RegisterDao | 5 | 2010-04-03 | 2010-06-03 | 4.5
|  | FertDao | 4 | 2010-08-03 | 2010-10-03 | 4
|  | InsDao | 4 | 20/3/2010 | 22/3/2010 | 3.5
|  | LoanDao | 4 | 24/3/2010 | 25/3/2010 | 3.5
|  | LocDao | 5 | 26/3/2010 | 28/3/2010 | 5
|  | PollDao | 4 | 29/3/2010 | 31/3/2010 | 4
|  | ToolDao | 4 | 2010-02-04 | 2010-04-04 | 4.5
|  | SoilDao | 3 | 2010-06-04 | 2010-06-04 | 2
|  | TrainingDao | 3 | 2010-07-04 | 2010-08-04 | 3.5
|  | LoginDao | 2 | 2010-10-04 | 2010-11-04 | 2.5
|  | CropDao | 5 | 405758 | 15/4/2010 | 6.5
|  | MarketDao | 4 | 18/4/2010 | 20/4/2010 | 4.5
|  | QueryDao | 3 | 21/4/2010 | 22/4/2010 | 3.5
|  |  | 50 |  |  | 51.5
|  |  | 135.5 |  |  | 139
| Literature Survey and Research |  |  |  |  | 20
| TOTAL |  |  | 2010-09-01 | 28/4/2010 | 159